## Slide 1: Implementation plan for Green Water Management Project in the dryland areas of Myanmar
Project Implementation Unit (PIU)
Department of Agriculture (DOA)
Ministry of Agriculture Livestock and Irrigation Nay Pyi Taw
16.9.2016
TA-REG 8163
Implementation of Core Agriculture Support Program
Phase II (CASP 2) Activities under LOA in Myanmar

## Slide 2: Background
CAPS 2 : will implement from 2011 to 2020
Phase II (CASP 2): Total Budget US$ 150,000
Vision of CASP 2 : For the GMS to be “recognized as the leading producer of safe food, using climate friendly agricultural practices and integrated into global markets through regional economic corridors”.
Inception Workshop
Site Selection
August 2016 – September 2016
LOA Signing
28 July 2016
Project Implementation
August 2016 – September 2017

## Slide 3: Objectives
To create green water management model in the dryland areas of Myanmar
To promote green water management awareness and best practices to local staffs and farmers through the efficient utilization of rainwater as supplementary water for the year round crops cultivation
To increase food security, food safety, households income and adaptive capacity of poor rural households to climate change and promote market linkages for smallholder farmers
To recommend policy makers for developing green water management in dryland areas of Myanmar

## Slide 4
  Map of Project Area

## Slide 5
  Project Implementation Arrangement

## Slide 6
Field visit for Site Selection

## Slide 7
Field visit for Site Selection

## Slide 8
Region | District | Township | Target Village | Total Population |  | Target beneficiaries | Target Demo farm | Target Pilot site
 |  |  |  | No. HH | No. person |  |  | 
Mandalay | Yemethin | Yemethin | Saegyi | 728 | 3625 | 50 | 1 | 1
Mandalay | Yemethin | Yemethin | Theingyone | 1645 | 7466 | 50 | 1 | 1
Mandalay | Yemethin | Pyawbwe | Satcho | 237 | 1440 | 50 | 1 | 1
Magway | Magway | Myo Thit | Thanngyone | 380 | 1698 | 50 | 1 | 1
Magway | Magway | Natmauk | Shwekwe | 162 | 678 | 50 | 1 | 1
Magway | Magway | Natmauk | Nakyarhtoo | 310 | 1408 | 50 | 1 | 1
Total | 2 Districts | 4 Townships | 6 villages | 3462 | 16315 | 300 | 6 | 6
List of target area, farm demonstration sites and pilot sites

## Slide 9
Project target area and beneficiaries
Implementing Partner | Beneficiaries |  |  | Target Areas |  |  | 
 | Farmer | Gov't officer | Private Sector/ INGOs | Region | District | Township | Village
Department of Agriculture (DOA), Land Use Division, Division of Horticulture, Vegetable and Biotechnology, Division of Project Planning and Management, NSSU under Department of Planning, Department of Irrigation and Water Resources Utilization Management, International Rice Research Institute (IRRI), Australia Center for International Agriculture Research (ACIAR), Groupe-de-Recherche-el-d’-Exchanges-Technologique (GRET), Organization for Industrial, Spiritual and Cultural Advancement-International (OISCA) Myanmar, Myanmar Farmers Association (MFA), Myanmar Fruit, and Vegetable Producers and Exporters Association (MFVPEA), Shan Maw Myae Co. Ltd Other Private Sector | 300 | 200 | 7 | 2 | 2 | 4 | 6

## Slide 10
Responsibility
Guidance, supervision and implementation of project activities in respective project site
Supporting the GWM technologies and materials for demonstration farm as well as pilot farmers
Practically conducting the demonstration farms for green water management
Organized by
Land Use Division and Department of Agriculture
Project Implementation Unit (PIU)

## Slide 11
No. | Position | Designation | Number
1. | Team Leader | Director, Land Use Division, DOA | 1
2. | Team Coordinator | Land Use Division, DOA | 1
3. | Team Group | Deputy Director, District level, DOA Staff Officer, Township Level, DOA Deputy Staff Officer, DOA Deputy Assistant Staff Officer, DOA | 2 4 4 6
Organization of PIU

## Slide 12: Project Implementation Body (PIB)
Responsibility
For implementing the project together with Demo farmers under the guidance of PIU.
Organized by
DOA extension staffs from respective townships

## Slide 13
Training Team will be collaborated with
Land Use Division
Plant Protection Division
Horticulture and Plant Biotechnology Division
Project Planning, Management and Evaluation Division
Subject Matter Specialist in Training Teams

## Slide 14: Monitoring and Evaluation
2-3 times during the implementation period in collaboration with a third party organization such as Yezin Agricultural University or other external associations

## Slide 15: Reporting Schedule
No. | Type of Report | Implementation Period | Submission Date PIU to NSSU | Submission Date NSSU to ADB
1 | Inception report | July – Aug 2016 | 25 Aug 2016 | end of Aug 2016
2 | First progress report (August to December 2016) | Aug – Dec 2016 | 01 Jan 2017 | 15 Jan 2017
3 | Second progress report (January to June 2017) | Jan – June 2017 | 01 July 2017 | 15 July 2017
4 | Third progress report (July to September 2017) | July – Sept 2017 | 01 Oct 2017 | 15 Oct 2017
5 | Final completion report | Aug 2016 – Sept 2017 | 01 Nov 2017 | 15 Nov 2017

## Slide 16: Planned activities
6 demonstration sites
Training for government officers (efficient utilization of rainwater, reducing agro-chemical use technologies and climate friendly agricultural practices)
50 trained officers will become as trainers
Training for 300 farmers (at least 25% women)
Supporting Biochar Kiln and other farm inputs
6 pilot projects (might be included about 20 pilot farmers)

## Slide 17
Ma Myint2 Mu’s Farm, Thangyone Village, Myothit Township

## Slide 18
Paddy
Paddy
Water pond
Eggplant or Tomato
Gliricidia or other trees
Farmer KC
Papaya
Onion leaves
Mango
Legume
Other vegetables
Model of GWM Demo Farm
Notes: Crop rotation

## Slide 19
U Thein Aung’s Farm, Nakyarhtoo Village, Natmauk Township

## Slide 20
U Mg Myint’s Farm, Segyi Village, Yemethin Township

## Slide 21
U Min Thet’s Farm, Theingyone Village, Yemethin Township

## Slide 22
Daw Tin Tin’s Farm, Setcho Village, Pyawbwe Township

## Slide 23
U Thein Hlaing’s Farm, Shwegwe Village, Natmauk Township

## Slide 24: Planned Activities
Capacity building trainings
Building farmer knowledge centres
Farmer field days and field visits
Construction of water pump system

## Slide 25: Capacity Building
For Demo-farmers
Green water management with climate friendly agriculture
Soil and water management practices
Good agricultural practices
Pre- and post- harvest technology
Introduction to participatory guarantee system

## Slide 26: Capacity Building
For Department of Agriculture (DOA) staffs:
Training to trainer for staffs from DOA on GWM through organic farming techniques and PGS
Project Management & Monitoring
Visit to six demo and pilot farms and discuss with demo and pilot farmers and other interested persons

## Slide 27: Supporting from the Project for the Farmers
Materials and inputs for demonstration farm
Materials for demonstration of GWM, solar pump, gliricidia or other trees, livestock and organic fertilizers such as Effective Microbes (EM) solution, Trichoderma, Dochekin, Vermiculture, Fish Amino Acid, Fermented Fruit Juice
Materials for botanical pesticides such as ginger, garlic, tobacco, plastic sheet, cow dung, rice bran

## Slide 28: Supporting from the Project for the Farmers
Activities at Farmer Knowledge Centre
Training for capacity building with pamphlets, hand books, vinyl posters, power point presentations, video shows , discussion and the practical
Farmer Field Days
Field Visit to demo farms as well as other private farms

## Slide 29
One national study and a report in English on policy support required on green water management and one national policy dialogue will be conducted
One national workshop to be organized to disseminate outcome of the project to stakeholders
Shared Myanmar’s best practices on green water management at the Regional Workshop
  Planned activities

## Slide 30
A water pumping system, Tatkone Township

## Slide 31: Expected Impact and Outcome
Impact
Improved agricultural land productivity and yield (20% increase) and Income (at least 20% increased) and safely products and to reduce poverty through income generation from GWM demonstration farm

## Slide 32: Expected Impact and Outcome
Outcome
Increased 20% in agricultural production
Increased at least 20% in income generation as their alternative livelihoods;
Market access and market demands for the Demo products will increase up to 20%
The target farmer’s income (demonstration and pilot farmers) will increase at least 20%
Support for national policy

## Slide 33
Thank you for your attention